## developmenttsd
DevelopmentTSD
Manage your individual project from this board. Set up tasks, owners, timelines, and more. See the aggregated data across your projects in the Portfolio Dashboard.
Akash QA
Name | Subtasks | Owner | Status | Timeline - Start | Timeline - End | Planned Effort | Actual Effort | Subtask effort | Completion Date | Completion Status | Item ID (auto generated)
Testing the system |  |  |  | 2023-04-24 | 2023-04-24 | 8 | 6 |  |  |  | 4478506715
Testing the system |  |  |  | 2023-04-25 | 2023-04-25 | 8 | 8 |  |  |  | 4478565313
Testing the system |  |  |  | 2023-04-26 | 2023-04-26 | 4 | 4 |  |  |  | 4478565405
Testing the Updated System |  |  |  | 2023-05-03 | 2023-05-03 | 8 | 8 |  |  |  | 4478647091
Testing the Updated System |  |  |  | 2023-05-04 | 2023-05-04 | 8 | 8 |  |  |  | 4478648254
Testing the Updated System |  |  |  | 2023-05-05 | 2023-05-05 | 4 | 4 |  |  |  | 4478648398
Testing the Updated System |  |  |  | 2023-05-10 | 2023-05-15 | 20 | 25 |  |  |  | 4478687025
|  |  |  | 2023-04-24 | 2023-05-15 |  |  |  |  | 0

## developmenttsd-updates
DevelopmentTSD | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
4478687025 | Testing the Updated System | Update |  | Akash Pradeep | 16/May/2023 01:04:02 PM | Have worked on Saturday 13-05-2023 | 0 |  | 2159009065